# Risk Assessment and Mitigation Plan

# Description

# A risk assessment and mitigation plan are a process for identifying and evaluating potential risks, and then developing strategies to reduce or eliminate the impact of those risks.

# Risk assessment

# Identify risks.

# Evaluate the potential impact of the risk.

# Prioritize risks.

# Risk mitigation

# Take actions to reduce the probability of risks occurring.

# Develop combinations of mitigation strategies.

| Risk | Potential Impact on Project Success (Low/Medium/High) | Probability of Occurrence (Low/Medium/High) | Mitigation Plan |
| --- | --- | --- | --- |
| Biomarker is not discovered | High | Low |  |
| Cell lines become contaminated | Medium | Medium | Thoroughly clean cell culture room. Go over sterile techniques with all persons using the cell culture room. |
| Personnel turnover (co-PI and/or research scientist leaves) | Low | Low |  |
| Unable to recruit participants | High | Medium | Hire a GRA to manage the recruitment and retention of participants. |

# Use economic tools to identify the most cost-effective combination of strategies.

# Example

# Additional Risk mitigation examples

# Planning and zoning.

# Floodplain protection.

# Property acquisition and relocation.

# Public outreach projects.

# Installing disaster warning systems.

# Purchasing radio communications equipment.

# Conducting emergency response train

Template [Copy and paste into your word document]

Instructions:

Step 1: Brainstorm possible risks.

Step 2: For each risk, assign a High/Medium/Low value for both potential impact and probability of occurrence on the project.

Step 3: Develop a mitigation plan for each High/High, High/Medium and Medium/High risk.

Consider developing mitigation plans for the Medium/Medium risks.

# Risk Assessment and Mitigation Plan

| Risk | Potential Impact on Project Success (Low/Medium/High) | Probability of Occurrence (Low/Medium/High) | Mitigation Plan (For all H/H, H/M and M/H risks. Recommended for M/M risks.) |
| --- | --- | --- | --- |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |